## Audit Results
Point | Quality Assurance Audit Checklist | Comply - Yes/No | P | Audit Date: 08/06/2022 | Task Link | Comply - Yes/No | P | Audit Date: 08/07/2022 | Task Link
|  | Project Management |  | 50.46% |  | Project Management |  | 73.39%
|  | Scrum Processes |  | 44.83% |  | Scrum Processes |  | 80.46%
|  | Quality Assurance |  | 34.78% |  | Quality Assurance |  | 78.26%
|  | Configuration Management |  | 60.94% |  | Configuration Management |  | 62.5%
|  | Product Management |  | 60.71% |  | Product Management |  | 66.07%
|  | Total Score |  | 49.35% |  | Total Score |  | 72.85%
Point | Checklist Items | Comply - Yes/No | P | Comments |  | Comply - Yes/No | P | Comments
PM | Project Management
5 | Traceability of the product features (EPIC) is established | Yes | 5 |  |  | Yes | 5
4 | Risk register created per release | No | 0 | Link |  | Yes | 4
4 | Project Risk Register updated weekly | No | 0 |  |  | Yes | 4
3 | Risk register is reviewed with team Regularly | No | 0 |  |  | Yes | 3
3 | Integration Plan prepared – List of platforms | Yes | 3 |  |  | Yes | 3
2 | Establish strategic training needs | No | 0 | Gather info form DEV |  | Yes | 4
5 | Project Specifications up to date | Yes | 2 | New info adding |  | Yes | 4
4 | Project Specifications updated weekly | Yes | 4 |  |  | No | 0
1 | Procurement Plan prepared | No | 0 |  |  | No | 0
1 | Vacation Plan prepared | No | 0 | Discuss |  | No | 0
3 | Project status report prepared weekly | Yes | 3 |  |  | Yes | 3
1 | Project status report reviewed by stakeholders weekly | Yes | 3 |  |  | No | 0
5 | Version and Release dates identified and compatible with product roadmap | Yes | 3 |  |  | Yes | 4
4 | Project Calendar reflects all release dates, milestones etc. | No | 0 |  |  | Yes | 4
3 | Release Notes created for each release | No | 0 | By email |  | Yes | 3
1 | Project has an organized page | No | 0 |  |  | No | 1
1 | All links are up to date | No | 0 |  |  | No | 1
1 | All people working on project are listed on the home page | No | 0 |  |  | No | 1
1 | Email groups for project set according to instruction | Yes | 1 |  |  | Yes | 1
5 | All items in backlog have an estimate | No | 0 |  |  | Yes | 3
5 | Product Backlog in a manageable size | No | 0 |  |  | Yes | 5
1 | Team have all people with a sufficient mix of skills to build a potentially shippable product increment | Yes | 1 |  |  | No | 0
3 | All dev tasks in sprint after deployment have version | Yes | 3 |  |  | Yes | 3
3 | Team does not over Commit (10% tolerance) – new high priority tasks appeared | No | 0 |  |  | No | 0
5 | There is no Critical and Major bugs in Backlog | Yes | 5 |  |  | No | 0
3 | Release Signoff process is applied | No | 0 |  |  | Yes | 3
4 | Release Signoff process applied and works properly | No | 0 |  |  | Yes | 3
3 | Components of project are up to date | Yes | 3 |  |  | Yes | 2
3 | All R&D team members informed about Development and QA process | Yes | 3 |  |  | No | 0
1 | Requirements to project DEV profile competence are ready | Yes | 1 |  |  | Yes | 1
1 | Requirements to project QA profile competence are ready | Yes | 1 |  |  | Yes | 1
1 | Requirements to all other profiles competence are ready | Yes | 1 |  |  | Yes | 1
5 | Internal SLA for customer requests created and up to date | Yes | 3 | Not approved new SLA with Support |  | Yes | 3
3 | Learning course for new DEV is up to date | Yes | 3 |  |  | Yes | 3
3 | Jira Workflow created and described with all statuses related | Yes | 3 |  |  | Yes | 3
2 | PM plan tasks for sprint based on initiatives priorities in AHA | Yes | 2 |  |  | Yes | 2
2 | Jira filters set according to the priority and severity | Yes | 2 |  |  | Yes | 2
4 | Plan of automation created based on ROI | No | 0 |  |  | No | 0
SM | Scrum Model
3 | Every User Story is written in the following way: “As <PERSONA>, I want <WHAT> so that <WHY>“. | No | 0 |  |  | Yes | 3
3 | Regular daily scrum meetings | Yes | 3 |  |  | Yes | 3
2 | In Daily Scrum Meeting team talk about only scrum agenda | No | 0 |  |  | Yes | 2
3 | Regular SP1 meetings | No | 0 |  |  | Yes | 3
0 | Regular SP2 meetings | Yes | 3 |  |  | N/A | 0
3 | Regular grooming meetings | Yes | 3 | Live discussion |  | Yes | 4
2 | Do team use poker card planning for estimation points | Yes | 2 |  |  | No | 0
2 | Regular review meetings (DEMO) | No | 0 |  |  | Yes | 2
2 | Regular retrospective meetings | No | 0 |  |  | No | 0
2 | Meeting Minutes created after Retrospective Meeting | Yes | 2 |  |  | No | 0
2 | Meeting Minutes created after Grooming Meeting | Yes | 2 |  |  | Yes | 2
3 | Solution Design Spec. created and modified iteratively | Yes | 3 |  |  | Yes | 3
3 | Every User Story has Acceptance Criteria and refers to Definition of Done (DoD) | No | 0 |  |  | No | 0
4 | Person who will accept the US is identified | No | 0 | For every task different |  | Yes | 4
4 | Every US is demonstrated at the end of sprint | No | 0 |  |  | Yes | 4
4 | Internal story dependencies are identified | Yes | 4 |  |  | Yes | 4
4 | External story dependencies are identified | Yes | 4 |  |  | Yes | 4
1 | Current sprint page up to date | No | 0 |  |  | No | 0
1 | Team have a sprint backlog – tickets planned for sprint | Yes | 1 |  |  | Yes | 1
3 | All items in sprint plan have an estimate | Yes | 3 |  |  | Yes | 3
2 | Every User Story has tasks related | Yes | 2 | Depend on size |  | Yes | 2
1 | Well defined DoD for R&D | No | 0 |  |  | Yes | 1
1 | Well defined DoD for QA | No | 0 |  |  | Yes | 1
2 | Test Reports up to date | No | 0 |  |  | Yes | 2
2 | Tasks and US's In Signed state have comments or merge request from executor | Yes | 2 |  |  | Yes | 2
5 | Progress reflection to JIRA board (Board Management) | No | 0 |  |  | Yes | 5
1 | Continuous Sprints | Yes | 1 |  |  | Yes | 1
1 | Sprint Naming – weeks numbers or dates | Yes | 1 |  |  | No | 0
2 | No Additional User Stories Can Be Added to the Sprint | No | 0 | only in case of low load |  | Yes | 2
2 | No Additional User Stories Can Be Added to the Sprint Outside the Project | No | 0 |  |  | No | 0
2 | Well defined Sprint Goal | No | 0 |  |  | No | 0
3 | Code Review for New feature development | Yes | 3 |  |  | Yes | 3
3 | Unit Testing for New feature development | No | 0 | Partly |  | Yes | 3
3 | Integration Test for New feature development | No | 0 |  |  | Yes | 3
1 | Tasks take no longer than one working day | No | 0 |  |  | No | 0
0 | On Time Code Freeze | N/A | 0 |  |  | Yes | 3
3 | Acceptance criteria for Sprint achievement | No | 0 |  |  | No | 0
2 | Acceptance criteria for Sprint achievement completed last sprint | No | 0 |  |  | No | 0
QA | Quality Assurance
4 | Every User Story has at least one User Acceptance Test | No | 0 |  |  | Yes | 4
3 | Every User Story in development has at least one User Acceptance Test | No | 0 |  |  | Yes | 3
3 | Every User Story in testing has at least one User Acceptance Test | No | 0 |  |  | Yes | 3
1 | Defects have summary | Yes | 1 |  |  | Yes | 1
1 | Defects have description? (Preconditions, Environment / Device/ OS, Test Steps, Expected Result, Actual, Result, TestRail link (Related Test Cases) Screen Shots) | No | 0 |  |  | Yes | 1
1 | Defects have release version | No | 0 |  |  | Yes | 1
1 | Defects have Priority | Yes | 1 |  |  | Yes | 1
1 | Defects have Component | Yes | 1 |  |  | Yes | 1
2 | Components are up to date | Yes | 1 |  |  | Yes | 1
2 | Defects have bug category | No | 0 |  |  | No | 0
2 | TestRail is used | Yes | 1 |  |  | Yes | 2
2 | Test cases created for each User Story (Preconditions, Test Steps, Expected Result) | No | 0 | Checklists |  | Yes | 2
5 | Test case automation is part of test case development | No | 0 |  |  | Yes | 3
1 | Test cases executed with a defined Test Run | No | 0 |  |  | No | 0
5 | End to End Test cases created and executed on the early stage | No | 0 | Plan with QA |  | Yes | 5
1 | Old test runs archived | No | 0 |  |  | No | 0
1 | Failed test cases associated with a Defect/Bug | No | 0 |  |  | Yes | 1
2 | Initial tests are executed in Stage Environment | Yes | 2 |  |  | Yes | 2
5 | Formal Tests (UAT, Smoke, Regression) are executed in Stage and Prod Environments | No | 0 | On Laravel |  | Yes | 5
3 | QA strategy/approach is up to date | Yes | 3 |  |  | Yes | 3
4 | Test plan up to date | Yes | 4 |  |  | Yes | 4
2 | Analysis of the bugs from the prod. environment | No | 1 | Personal check or Scrum |  | Yes | 2
2 | Analysis of the bugs from the Stage environment (UAT, Smoke, Regression) | No | 0 |  |  | Yes | 2
1 | All QA team members have been informed about Development and QA process | Yes | 2 |  |  | No | 0
3 | Test case estimations | No | 0 |  |  | No | 0
5 | Every critical functionality have automated test | Yes | 4 |  |  | Yes | 4
3 | Load tests run automatically | No | 0 | No load tests |  | No | 0
3 | All automatic emails can be sent to delined email for quality checking | Yes | 3 | In archieve |  | Yes | 3
CM | Configuration Management
2 | Development Environment is ready | Yes | 2 |  |  | Yes | 2
2 | Source control environment is ready | Yes | 2 | Git, BitBucket |  | Yes | 2
3 | GIT branching model is adapted (Development in dev-branch, releases in master branch) | Yes | 3 |  |  | Yes | 3
3 | Continuous Integration (CI) is up and running | Yes | 3 | In APP |  | No | 0
2 | Test Environments are ready | Yes | 2 |  |  | Yes | 2
2 | Stage Environment is ready and described | Yes | 2 | Branches can be deployed separatelly |  | Yes | 2
2 | Deployment Strategy is ready | No | 0 |  |  | Yes | 2
3 | Configuration Management plan up to date | No | 0 |  |  | No | 0
3 | Configuration Management plan is reviewed with team | No | 0 |  |  | No | 0
3 | Running Unit test in CI | Yes | 3 | Every deploy |  | Yes | 3
2 | Running Integration Test in CI | No | 0 |  |  | Yes | 2
3 | Running Functional Test in CI | Yes | 3 |  |  | Yes | 3
3 | Ready for Continuous Delivery | Yes | 3 |  |  | Yes | 3
2 | Requirements to the Environment and it's setting are ready | No | 0 |  |  | No | 0
1 | List of sub-systems is up to date and every system well described | No | 0 |  |  | No | 0
2 | Product architecture described in separate doc with all modules detales | No | 0 |  |  | No | 0
1 | Release version set in Jira | No | 0 | For APP - need to be done manualy - new changes go to Prod ASAP |  | No | 0
1 | Integration with Jira - SmartCommits | No | 0 |  |  | No | 0
2 | Static code analysys in IDE for every pull-request | No | 0 | Task in plans |  | No | 0
3 | Development Environment can be created in 2 hours | Yes | 3 | For Laravel in progress |  | Yes | 3
4 | Autotests run with defined pass rate before QA | No | 1 | Alure on APP |  | No | 1
1 | Analysys of formatting in IDE | Yes | 1 | Basic settings in IDE |  | Yes | 1
3 | Prod enviroment config equal to Stage | Yes | 3 |  |  | Yes | 3
3 | Deployed tasks sent to "release@" | No | 1 | APP only - for admins |  | No | 1
3 | Backup\Restore systems created and working properly | Yes | 3 | Daily |  | Yes | 3
3 | Monitoring system created and working properly | Yes | 3 | All servers been monitored |  | Yes | 3
2 | Access to every system personilized (SSH, BD, Jira, AHA, Passwords etc.) | Yes | 1 | BD access not personalized, TestRail |  | Yes | 1
PdM | Product Management
3 | Product vision ready | Yes | 3 |  |  | No | 0
2 | Product vision confirmed and taken to account on goals setting | Yes | 2 |  |  | No | 0
3 | Product Roadmap ready | Yes | 3 |  |  | Yes | 3
2 | Product Roadmap confirmed and public | Yes | 2 |  |  | Yes | 2
3 | Product Roadmap up to date | Yes | 3 |  |  | Yes | 3
3 | Product features listed and detailed | Yes | 3 |  |  | Yes | 3
3 | Participating grooming meetings | No | 0 |  |  | Yes | 3
3 | Participating review meetings | Yes | 3 |  |  | Yes | 3
3 | Participating Sprint Planning meetings | Yes | 3 |  |  | Yes | 3
5 | Using Prioritizing method for backlog prioritizing | No | 0 |  |  | No | 0
5 | Regular backlog prioritizing | No | 0 |  |  | Yes | 5
2 | List of 5 main competitors described in details | Yes | 2 |  |  | Yes | 2
2 | Profiles of 5 main users of the product filled in | Yes | 2 |  |  | Yes | 2
2 | Goals and initiatives described according to SMART and INVEST | No | 0 |  |  | No | 0
2 | Portal of ideas created in AHA | Yes | 2 |  |  | Yes | 2
2 | All ideas are up to date and in actual statuses | Yes | 2 |  |  | Yes | 2
2 | All features linked to goals and initiatives | Yes | 2 |  |  | Yes | 2
2 | Releases contatins the most important features and planned 3 month ahead | No | 0 |  |  | No | 0
2 | Automatic creating of Jira ticket on critical error | No | 0 |  |  | No | 0
3 | Created SLA on critical error | No | 0 | No docs |  | No | 0
2 | Plan for 6 month ready | Yes | 2 |  |  | Yes | 2
|  |  | 08/06/2022 | 08/07/2022
|  | Project Management | 50.46% | 73.39%
|  | Scrum Processes | 44.83% | 80.46%
|  | Quality Assurance | 34.78% | 78.26%
|  | Configuration Management | 60.94% | 62.5%
|  | Product Management | 60.71% | 66.07%
|  | Total Score | 49.35% | 72.85%

## Instruction
QA audit should be done in the next situations:
1) Some problems with quality
2) Process problems
3) Unification needs
4) Passion to grow and work better
5) Necessity to improve maturity level of company and projects
What effect will you get:
1) Transparency improvement
2) Understanding of real situation
3) Defined system of mectics
4) Results analysis
5) Correction influence
6) Metrics of result
7) Control of "not degradation"
How to use:
1) Find responsible person - the best is Project/Product manager
2) Schedule the meeting for 1-2 hours and set Audit Date (column "E" row "1")
3) Went through all the points of audit
4) Calibrate every points regarding the weight - 1-5 (column "A")
5) Set preliminary mark Yes/No (column "C") and set comments or tasks to improve
6) It can be set partly as "No" with 1-2 points (column "D") and comment (column "E")
7) After completing all marks there will be result in "%" per every area (column "D" rows "170-175")
8) It will reflects in Bar Chart and under Audit Date (column "D" rows "2-7")
9) On new audit you can add 4 columns after column F and copy columns "C"-"F" there to change date and run new audit
10) Then update Bar Chart with new data and you'll see the progress
11) After getting results define areas and points to improve and set exact tasks for that in Task Management System and set links to tasks in appropriate cells